## Sheet 1 - Gantt chart For MM_SC
Gantt chart For MM:SC Date: April 19, 2021-May 14th, 2021
Description of Task | Task Belongs To: | Start Date: | End Date: | Duration | Completion Percentage | Week 1 April 19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | Week 2 April 26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | Week 3 May 3 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | Week 4 May 10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14
Discussed and Created Trello Kanban Board | Everyone | 2021-04-19 | 2021-04-25 | 6 | 100%
Shared Existing Work | Everyone | 2021-04-19 | 2021-04-26 | 7 | 100%
Updated Player Art to Turn 4 more Directions and be Animated | Stephanie | 2021-04-26 | 2021-04-28 | 2 | 100%
Updated Generic Monster Art to be Animated | Stephanie | 2021-04-26 | 2021-04-28 | 2 | 100%
Added Boss Monster Move Left and Right Animation | Stephanie | 2021-04-26 | 2021-04-28 | 2 | 100%
Added New Art to Game | Jose | 2021-04-26 | 2021-05-02 | 6 | 100%
Added Art for Game Over Screen | Nikki | 2021-04-26 | 2021-05-02 | 6 | 100%
Implemented Healthbar | Jose | 2021-04-26 | 2021-05-02 | 6 | 100%
Implemented Title Screen, How To Play Screen, and Functional Buttons | Nikki | 2021-04-26 | 2021-05-02 | 6 | 100%
Added Progression Script for Moving Through Different Scenes in Game | Nikki | 2021-04-26 | 2021-05-02 | 6 | 100%
Added Script for picking up health, and adding health | Nikki | 2021-04-26 | 2021-05-03 | 7 | 100%
Fixed Healthbar to Display Correctly at Full Health | Nikki | 2021-04-26 | 2021-05-03 | 7 | 100%
Fixed Art Going Wrong Direction in Game | Jose | 2021-05-03 | 2021-05-04 | 1 | 100%
Added Enemy Flash Red on Attack | Nikki | 2021-05-03 | 2021-05-04 | 1 | 100%
Added Fire Rate Limiter on Player Weapon | Jose | 2021-05-03 | 2021-05-04 | 1 | 100%
Added New Tilesets Art | Dante | 2021-05-03 | 2021-05-05 | 2 | 100%
Adjusted Sprite Art | Dante | 2021-05-03 | 2021-05-06 | 3 | 100%
Mapped Tile for Level 2 | Jose | 2021-05-03 | 2021-05-06 | 3 | 100%
Mapped Tile for Level 3 | Jose | 2021-05-06 | 2021-05-10 | 4 | 100%
Added Lighting and Weather for Level 2 | Jose | 2021-05-06 | 2021-05-10 | 4 | 100%
Added Lighting and Weather for Level 3 | Jose | 2021-05-06 | 2021-05-10 | 4 | 100%
Added Alternate Enemy | Jose | 2021-05-10 | 2021-05-11 | 1 | 100%
Added Picking Up Items (Health, Ammo, Objective Item) | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Game Over Art to Game Over Screen | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Art for Ammo, Health, Objective Marker, and Objective Items | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Art for Boss moving Up, Down, and Death Sequence | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Replaced Temp Images for Health, Ammo, and Objective Items with Art | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Objective Markers for Level 2 | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Objective for Level 2 | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Objective for Level 3 | Nikki | 2021-05-10 | 2021-05-12 | 2 | 100%
Added Boss to Level 3 | Nikki | 2021-05-10 | 2021-05-13 | 3 | 100%
Adjusted Win Game Criteria | Jose | 2021-05-10 | 2021-05-13 | 3 | 100%
Adjusted Timer for Level 3 | Jose | 2021-05-10 | 2021-05-14 | 4 | 100%